## Job Desc
No | Nama Kegiatan | Detail | Penanggung Jawab | Status
1 | Database Design |  | Teguh Dwi Cahyo | Done
2 | Preprocessing Data |  | Teguh Dwi Cahyo | Done
3 | Modelling | Model CNN 1 | Muhammad Farhan Anwari | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | Done
4 | Model Inference |  | Muhammad Farhan Anwari | waiting
5 | Model Evaluation |  | Muhammad Farhan Anwari | waiting
6 | Prediksi Data |  | Teguh Dwi Cahyo | waiting
7 | Frontend Web |  | Muhammad Farhan Anwari | waiting
8 | Backend Web |  | Teguh Dwi Cahyo | waiting
9 | Deployment |  | Teguh Dwi Cahyo | waiting
10 | Testing |  | Muhammad Farhan Anwari | waiting

## Jadwal Pengerjaan
No | Nama Kegiatan | Detail | Penanggung Jawab | Target Mulai | Target Penyelesaian | Status
1 | Database Design |  | Teguh Dwi Cahyo | 2021-10-22 | 2021-10-24 | Done
2 | Preprocessing Data |  | Teguh Dwi Cahyo | 2021-10-22 | 2021-10-24 | Done
3 | Modelling | Model CNN 1 | Muhammad Farhan Anwari | 2021-10-22 | 2021-10-25 | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | 2021-10-22 | 2021-10-25 | Done
4 | Model Inference |  | Muhammad Farhan Anwari |  |  | waiting
5 | Model Evaluation |  | Muhammad Farhan Anwari |  |  | waiting
6 | Prediksi Data |  | Teguh Dwi Cahyo |  |  | waiting
7 | Frontend Web |  | Muhammad Farhan Anwari |  |  | waiting
8 | Backend Web |  | Teguh Dwi Cahyo |  |  | waiting
9 | Deployment |  | Teguh Dwi Cahyo |  |  | waiting
10 | Testing |  | Muhammad Farhan Anwari |  |  | waiting