## Job Desc Revisi
No | Nama Kegiatan | Detail | Penanggung Jawab | Status
1 | Database Design | Pembagian dataset: -Train : 70% dan Validation : 30% | Teguh Dwi Cahyo | Done
|  | Pembagian dataset: -Train : 80% , Validation : 19%, Test : 1% | Teguh Dwi Cahyo | Done
2 | Preprocessing Data | Preprocessing Manual | Teguh Dwi Cahyo | Done
|  | Preprocessing dengan Image Data Generator | Teguh Dwi Cahyo | Done
3 | Modelling | Model CNN 1 | Muhammad Farhan Anwari | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | Done
|  | Model CNN 3 | Muhammad Farhan Anwari | Done
|  | Model CNN 4 | Teguh Dwi Cahyo | Done
|  | Model CNN 5 | Muhammad Farhan Anwari | Done
|  | Model CNN 6 | Teguh Dwi Cahyo | Done
|  | Model CNN with TL | Teguh Dwi Cahyo | Done
Muhammad Farhan Anwari
4 | Model Inference | All Model | Bersama | Done
5 | Model Evaluation | All Model | Bersama | Done
6 | Frontend Web | All Model | Muhammad Farhan Anwari | waiting
7 | Backend Web | All Model | Teguh Dwi Cahyo | waiting
8 | Deployment | All Model | Teguh Dwi Cahyo | waiting
9 | Testing | All Model | Muhammad Farhan Anwari | waiting

## Jadwal Pengerjaan
No | Nama Kegiatan | Detail | Penanggung Jawab | Mulai | Target Penyelesaian | Penyelesaian | Status
1 | Database Design | Pembagian dataset: -Train : 70% dan Validation : 30% | Teguh Dwi Cahyo | 2021-10-22 | 2021-10-24 | 2021-10-24 | Done
|  | Pembagian dataset: -Train : 80% , Validation : 19%, Test : 1% | Teguh Dwi Cahyo | 2021-11-06 | 2021-11-08 | 2021-11-08 | Done
2 | Preprocessing Data | Preprocessing Manual | Teguh Dwi Cahyo | 2021-10-22 | 2021-10-24 | 2021-10-24 | Done
|  | Preprocessing dengan Image Data Generator | Teguh Dwi Cahyo | 2021-11-06 | 2021-11-08 | 2021-11-08 | Done
|  | Preprocessing dengan Image Data Generator dan Balancing Dataset | Muhammad Farhan Anwari | 2021-11-26 | 2021-11-27 | 2021-11-28 | Done
|  | Preprocessing dengan Image Data Generator dan Balancing Dataset | Muhammad Farhan Anwari | 2021-12-10 | 2021-12-11 | 2021-12-12 | Done
3 | Modelling | Model CNN 1 | Muhammad Farhan Anwari | 2021-10-22 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | 2021-10-22 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 3 | Muhammad Farhan Anwari | 2021-11-06 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 4 | Teguh Dwi Cahyo | 2021-11-09 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 5 | Muhammad Farhan Anwari | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN 6 | Teguh Dwi Cahyo | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN with TL | Teguh Dwi Cahyo | 2021-12-11 | 2021-12-14 | 2021-12-24 | Done
|  | Model CNN with TL | Muhammad Farhan Anwari | 2021-12-11 | 2021-12-14 | 2021-12-24 | Done
4 | Model Inference | Model CNN 1 | Muhammad Farhan Anwari | 2021-10-25 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | 2021-10-25 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 3 | Muhammad Farhan Anwari | 2021-11-09 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 4 | Teguh Dwi Cahyo | 2021-11-09 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 5 | Muhammad Farhan Anwari | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN 6 | Teguh Dwi Cahyo | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN with TL | Teguh Dwi Cahyo | 2021-12-11 | 2021-12-14 | 2021-12-24 | Done
|  | Model CNN with TL | Muhammad Farhan Anwari | 2021-12-12 | 2021-12-14 | 2021-12-24 | Done
5 | Model Evaluation | Model CNN 1 | Muhammad Farhan Anwari | 2021-10-25 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 2 | Muhammad Farhan Anwari | 2021-10-25 | 2021-10-25 | 2021-10-25 | Done
|  | Model CNN 3 | Muhammad Farhan Anwari | 2021-11-09 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 4 | Teguh Dwi Cahyo | 2021-11-09 | 2021-11-09 | 2021-11-09 | Done
|  | Model CNN 5 | Muhammad Farhan Anwari | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN 6 | Teguh Dwi Cahyo | 2021-11-28 | 2021-11-30 | 2021-12-03 | Done
|  | Model CNN with TL | Teguh Dwi Cahyo | 2021-12-11 | 2021-12-14 | 2021-12-24 | Done
|  | Model CNN with TL | Muhammad Farhan Anwari | 2021-12-12 | 2021-12-14 | 2021-12-24 | Done
6 | Frontend Web | All Model | Muhammad Farhan Anwari | 2021-12-17 | 2021-12-23 |  | Done
7 | Backend Web | All Model | Teguh Dwi Cahyo | 2021-12-17 | 2021-12-23 |  | waiting
8 | Deployment | All Model | Teguh Dwi Cahyo | 2021-12-17 | 2021-12-23 |  | waiting
9 | Testing | All Model | Muhammad Farhan Anwari | 2021-12-23 | 2021-12-23 |  | waiting